



M1 Report

Status Report for Milestone 1

Chris Field | Eric Foertsch | Jason Tierney

2013

### Intended Progress

We use the SCRUM development process to determine our workload and tasks we want to accomplish during specific periods of time. This allows us to easily determine where we stand as far as being on schedule or not.

At this point in the project we anticipated getting ready to release our Minimal Viable Product (MVP). The MVP would be released to the Windows Store after it was approved. We wanted the MVP to include three major categories: Professors, News, and Events pages for the GVSU School of CIS. We also had stretch goals which included incorporating the GVSU School of CIS’s YouTube channel in the app as well. The intended was also to include live data feeds for each of our pages. Some of the key items we hoped to have accomplished by this milestone include the following:

* Create a Minimal Viable Product and submit it to the Windows Store
  + Create Professor, News, and Events sections
* Learn about Windows Store application development
* Attach to backend services
* Create a YouTube video section (stretch goal)

The last goal on the list is defined as a stretch goal. This goal means we would like to accomplish it if every other goals was accomplished first.

### Progress to Date

We were able to create an MVP by the fifth week and we submitted the app to the Windows Store. The app is currently under the review process in the Windows Store. The first submission failed due to not having a privacy policy. This was remedied and the app was resubmitted to the Windows Store. As of this point we have accomplished the following goals:

* Created a section for the Professors/Faculty
* Created the news page
* Created the events page
* Submitted our MVP to the Windows Store
* Learned about the Windows Store app submission process
* Learned how to develop Windows Store apps

However, some of our goals were not accomplished as of this milestone. Two main goals were not accomplished, one of which was a stretch goal:

* Live data feeds for each section
* YouTube video section (stretch goal)

### Projected Progress

As it stands, we already have a few goals we would like to accomplish by milestone 2. Below is a list with explanations of the goals we would like to have accomplished.

**Code cleanup / Refactoring.** Over the next week we are planning to overhaul a lot of the back end code. Cleaning up this code will result in a more efficient and effective platform in the long run.

**Create Service Classes.** The next week (2/25 – 3/1) we are planning on creating backend service classes which will help feed the data to our application.

**Create backend data services.** The eighth/ninth weeks (3/4 – 3/15) we plan on creating our backend data services. This will be an ambitious goal and may require 1-2 weeks to accomplish. Because this sprint will overlap with spring break, we feel very confident we could use that time to accomplish these goals in those two weeks.

### Conclusion

As a group, we feel like we have achieved most of the goals we initially set forth up to the M1 release. At this point, we do not feel like we will have any trouble accomplishing future goals from now until the M2 release. A lot of our time in the first five weeks was spent learning the technologies and services that we needed to use in order to create the initial MVP.