## Slide 1: TEAM Microsoft
M1 Status Report – January 7 – February 15, 2013

## Slide 2: Intended Progress
Learn Windows Store app development
Create a Minimal Viable Product (MVP)
  Professor/Faculty, News, and Events sections
Submit MVP to Windows Store
Learn about the submission process
Connect to live data feeds
Create a YouTube video section (stretch)

## Slide 3: Actual Progress
Learned Windows Store app development
Created a Minimal Viable Product (MVP)
  Professor/Faculty, News, and Events sections
Submitted MVP to Windows Store
  Successful – we now have an app in the Windows Store!
Learned about the submission process

## Slide 4: Missed Goals/Targets
Connect to live data feeds
Create a YouTube video section (stretch)

## Slide 5: Reasons for missed goals
Procrastination
Learning the services / technologies of Windows Store apps
Data feeds did not work as expected

## Slide 6: Future Progress
M2 (February 18 – March 15)
Code cleanup / refactoring (Release Sprint 1 – Feb 18 – 22)
Create Service Classes (Release Sprint 2 – Feb 25 – Mar 1)
Create backend data services (Release Sprint 3 – Mar 4 – Mar 15)

## Slide 7: Thoughts?
Feel confident about future goals
Weekly sprints allow to keep track of progress
TFS / SCRUM diagrams

## Slide 8: Q & A Time